## Gantt Chart
	TCC – Previsor de Renda				56%
	[Company]
	[Project Manager]		segunda-feira, 22 de setembro de 2025

										32					33					34					35					36					37					38					39					40					41					42					43					44					45					46					47					48					49					50					51					52					53					01					02					03					04
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	ago-25					set-25					out-25					nov-25					dez-25					jan-26
			02-ago-2025	359	17-dez-2026	56%	503			02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29
	AnteProjeto	[name]	02-ago-2025	60	24-out-2025	56%	84	18	19
	Planejamento e Organização		02-ago-2025
	Revisão bibliográfica	[name]	03-ago-2025	9	13-ago-2025	100%	11	9	0
	Estudo da PNAD Contínua	[name]	22-set-2025	9	02-out-2025	40%	11	3	6
	Definição das variáveis	[name]	02-out-2025	5	08-out-2025	50%	7	2	3
	Requisitos funcionais	[name]	13-out-2025	3	15-out-2025	50%	3	1	2
	Requisitos não funcionais	[name]	15-out-2025	3	17-out-2025	50%	3	1	2
	Regras de negócio	[name]	17-out-2025	3	21-out-2025	50%	5	1	2
	Declaração do Escopo	[name]	20-out-2025	5	24-out-2025	20%	5	1	4
	Estrutura		30-dez-2025

	Projeto de diplomação 1	[name]	01-fev-2026	10	13-fev-2026	45%	13	3	7
	Coleta e Preparação de Dados	[name]	01-fev-2026
	Microdados PNAD	[name]	02-fev-2026	5	06-fev-2026	55%	5	2	3
	Estruturação inicial	[name]	09-fev-2026	5	13-fev-2026	35%	5	1	4
	Tratamento de valores ausentes	[name]	19-fev-2026	3	23-fev-2026	0%	5	0	3
	Correção de formatos	[name]	24-fev-2026	3	26-fev-2026	0%	3	0	3
	Remoção de duplicados	[name]	27-fev-2026	3	03-mar-2026	0%	5	0	3
	Outliers tratados	[name]	04-mar-2026	9	16-mar-2026	0%	13	0	9
	Codificação categóricas	[name]	17-mar-2026	5	23-mar-2026	0%	7	0	5
	Dataset final	[name]	24-jun-2026	5	30-jun-2026	0%	7	0	5
	Coleta e Preparação de Dados	[name]	25-mar-2026
	Seleção de algoritmos	[name]	29-mar-2026	5	02-abr-2026	12%	5	0	5
	Pré-processamento e split (Regressão Linear)	[name]	09-abr-2026	3	13-abr-2026	30%	5	0	3
	Treinamento (Regressão Linear)	[name]	14-abr-2026	3	16-abr-2026	0%	3	0	3
	Avaliação inicial (Regressão Linear)	[name]	17-abr-2026	3	21-abr-2026	0%	5	0	3
	Pré-processamento e split (Random Forest)	[name]	23-abr-2026	3	27-abr-2026	30%	5	0	3
	Treinamento (Random Forest)	[name]	28-abr-2026	3	30-abr-2026	0%	3	0	3
	Avaliação inicial (Random Forest)	[name]	04-mai-2026	3	06-mai-2026	0%	3	0	3
	Pré-processamento e split (Gradient Boosting)	[name]	07-mai-2026	3	11-mai-2026	30%	5	0	3
	Treinamento (Gradient Boosting)	[name]	12-mai-2026	3	14-mai-2026	0%	3	0	3
	Avaliação inicial (Gradient Boosting)	[name]	15-mai-2026	3	19-mai-2026	0%	5	0	3
	Execução da validação	[name]	20-mai-2026	3	22-mai-2026	45%	3	1	2
	Cálculo das métricas	[name]	25-mai-2026	3	27-mai-2026	75%	3	2	1
	Visualização dos resultados	[name]	28-mai-2026	3	01-jun-2026	80%	5	2	1
	Modelo final	[name]	02-jun-2026	5	08-jun-2026	75%	7	3	2
	Documentação da modelagem	[name]	09-jun-2026	5	15-jun-2026	15%	7	0	5

	Projeto de diplomação 2	[name]	16-jun-2026	15	06-jul-2026	75%	21	9	5
	Backend (API Previsor)	[name]	16-jun-2026
	Estrutura backend	[name]	17-jun-2026	9	29-jun-2026	75%	13	6	3
	Endpoint predict	[name]	30-jun-2026	5	06-jul-2026	75%	7	3	2
	Métricas e logs	[name]	07-jul-2026	5	13-jul-2026	75%	7	3	2
	Cache de previsões	[name]	14-jul-2026	5	20-jul-2026	75%	7	3	2
	Failover baseline	[name]	21-jul-2026	5	27-jul-2026	75%	7	3	2
	Testes unitários	[name]	28-jul-2026	5	03-ago-2026	75%	7	3	2
	Testes de integração	[name]	04-jul-2026	5	09-jul-2026	75%	6	3	2
	Documentação da API	[name]	10-jul-2026	5	16-jul-2026	75%	7	3	2
	Frontend (Interface)	[name]	17-jul-2026
	Projeto React.js	[name]	18-jul-2026	5	23-jul-2026	75%	6	3	2
	Formulário de perfil	[name]	24-jul-2026	9	05-ago-2026	75%	13	6	3
	Validações no formulário	[name]	07-ago-2026	5	13-ago-2026	75%	7	3	2
	Integração com backend	[name]	14-ago-2026	9	26-ago-2026	75%	13	6	3
	Pagina do Formulario	[name]	27-ago-2026	9	08-set-2026	75%	13	6	3
	Responsividade e acessibilidade	[name]	09-set-2026	5	15-set-2026	75%	7	3	2
	Exportação de resultados	[name]	16-set-2026	5	22-set-2026	75%	7	3	2
	Testes frontend	[name]	21-set-2026	9	01-out-2026	75%	11	6	3
	Integração e Testes Finais	[name]	02-out-2026
	Integração total	[name]	03-out-2026	9	14-out-2026	75%	12	6	3
	Testes de desempenho	[name]	15-out-2026	5	21-out-2026	75%	7	3	2
	Testes de usabilidade	[name]	22-out-2026	5	28-out-2026	75%	7	3	2
	Correções finais	[name]	29-out-2026	9	10-nov-2026	75%	13	6	3
	Artefatos Acadêmicos	[name]	11-nov-2026
	Relatório técnico	[name]	12-nov-2026	9	24-nov-2026	75%	13	6	3
	Testes de desempenho	[name]	25-nov-2026	5	01-dez-2026	75%	7	3	2
	Testes de usabilidade	[name]	02-dez-2026	3	04-dez-2026	75%	3	2	1
	Encerramento	[name]	04-dez-2026
	Relatório técnico	[name]	05-dez-2026	5	10-dez-2026	75%	6	3	2
	Testes de desempenho	[name]	11-dez-2026	5	17-dez-2026	75%	7	3	2

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		01/01/14
		04/03/14
		18/04/14
		20/04/14
		25/04/14
		01/05/14
		10/06/14
		15/08/14
		08/12/14
		25/12/14